## Single Boat BOM
OPEN SOURCE RACING NAVIGATION SYSTEM — SINGLE BOAT SOURCING SHEET
Priority: P1 = order immediately (prototype start) ¦ P2 = order after P1 validated ¦ P3 = optional/premium/later
# | Item | Part / Model | Supplier | Link / Search Term | Qty | Unit £ | Total £ | Lead Time | Priority | Notes | Status
MASTHEAD ASSEMBLY — Wind speed & direction
1 | Ultrasonic anemometer (NMEA 0183 out) | Veinasa CXS02B-N | AliExpress / Veinasa | AliExpress: search 'Veinasa CXS02B-N NMEA' | 1 | 155 | 155 | 3-4 wks | P1 | The core sensor. $199 on AliExpress. Specify NMEA 0183 output when ordering (not RS485 or SDI-12). Ask for aluminium housing not ABS if available. Get 4Hz firmware if offered.
2 | Spare anemometer (break/test unit) | Veinasa CXS02B-N | AliExpress / Veinasa | AliExpress: search 'Veinasa CXS02B-N NMEA' | 1 | 155 | 155 | 3-4 wks | P2 | Essential. One for development/testing on the bench (you WILL destroy it during lab hardening experiments), one for the boat. At 30-boat scale, order spares at 10% of fleet size.
3 | IP68 cable gland (M16, 6-12mm cable) | Bimed M16 IP68 | RS Components | RS stock no 484-7094 or similar | 1 | 3.5 | 3.5 | 1-2 days | P1 | Replaces the Chinese OEM gland which is the #1 water ingress point. Get the right size for your cable OD.
4 | Marine shielded 4-core cable, 20m | Oceanflex 4-core 0.75mm² tinned | ASAP Supplies / chandler | ASAP: 4-core tinned marine cable | 1 | 55 | 55 | 2-3 days | P1 | Tinned copper, marine grade. Runs mast to below-deck sensor box. NMEA 0183 needs only 2 signal + 2 power cores, 0.75mm² handles the power draw easily.
5 | Masthead mounting bracket | Generic stainless steel | Force 4 / chandler / 3D print | Search 'masthead wind instrument bracket' | 1 | 30 | 30 | 1 wk | P2 | The Veinasa comes with a flat base. You need a bracket to offset it from the backstay and keep it level. Lab can 3D print in PETG initially.
6 | Conformal coating spray | MG Chemicals 422B (340g) | RS / Farnell | RS stock no 186-0851 | 1 | 15 | 15 | 1-2 days | P1 | Urethane coating for internal PCB. Breathable enough to let moisture out but stops corrosion. Standard in marine/aerospace.
7 | Marine polyurethane potting compound | Sika SikaBiresin CR82 or equivalent | RS / Farnell / Sika | RS: search 'polyurethane potting compound' | 1 | 28 | 28 | 1 wk | P1 | Fill internal air voids. Don't use epoxy — it's rigid and cracks with thermal cycling. PUR flexes.
8 | Silica gel desiccant packs | 1g indicator packs x 50 | Amazon | Amazon: 'silica gel packets indicator' | 1 | 6 | 6 | 1-2 days | P1 | Go inside every sealed enclosure. Indicator (blue-to-pink) lets you tell when they need replacing.
[6 empty] | Section subtotal: | 447.5
HULL ASSEMBLY — Depth sounder (DIY Open Echo path)
9 | 200 kHz ultrasonic transducer, 19mm piezo | Generic AliExpress fish finder xducer | AliExpress | AliExpress: '200khz transducer fish finder' | 1 | 12 | 12 | 3-4 wks | P1 | The exact part used successfully on the Open Echo project (github.com/Neumi/open_echo). Buy 3 — cheap, you'll destroy some in potting experiments.
10 | TUSS4470 ultrasonic driver IC | Texas Instruments TUSS4470 | Mouser / Digi-Key | Mouser: TUSS4470DDAR | 3 | 6.5 | 19.5 | 1 wk | P1 | The driver/receiver chip at the heart of the sonar board. Buy 3-5 for build + spares — they're sensitive to over-voltage during prototyping.
11 | Arduino Nano (or ESP32 variant) | Arduino Nano clone (ATmega328P) | AliExpress / The Pi Hut | AliExpress: 'Arduino Nano clone' | 2 | 5 | 10 | 2-3 wks | P1 | MCU for the sonar board. Per the Open Echo project. ESP32 works too if you want wifi-native; Nano is simpler.
12 | MT3608 boost converter module | Generic MT3608 2A step-up | AliExpress | AliExpress: 'MT3608 boost converter' | 2 | 2 | 4 | 2-3 wks | P1 | Boosts 5V USB to the 15-20V drive voltage the TUSS4470 needs for transducer drive.
13 | Custom PCB — Open Echo shield (5 boards) | JLCPCB standard 2-layer | JLCPCB | jlcpcb.com (use Open Echo Gerbers) | 1 | 18 | 18 | 2 wks inc. ship | P2 | Order after you've built a breadboard prototype. Open Echo publishes Gerbers on GitHub. 5 boards is the min order and costs basically the same as 2.
14 | Plastic thru-hull depth housing | Airmar low-profile or generic plastic | Force 4 / ASAP | Force4: 'thru-hull transducer housing' | 1 | 28 | 28 | 3-5 days | P2 | The marine-grade housing that goes through the hull. Generic plastic ones (not branded) are fine for ~20m depth use. Includes internal threaded fitting.
15 | Marine epoxy (transducer bonding) | West System 105/206 or Loctite EA E-60HP | chandler / RS | Force4: 'West System epoxy' | 1 | 12 | 12 | 1-2 days | P2 | Bonds the transducer into the housing with an acoustic-transparent layer. Regular epoxy is fine acoustically at 200kHz.
16 | ALTERNATIVE: Pre-built Chinese depth transducer | OVA A-P319N NMEA 0183 | Saiyang Marine (Alibaba) | Alibaba: 'OVA A-P319N' | 0 | 105 | 0 | 3-4 wks | P3 | If the DIY route is too much work, this is a drop-in ready NMEA 0183 depth transducer from China at £100 vs £700+ Airmar. Set qty 0 if building DIY.
[6 empty] | Section subtotal: | 103.5
SENSOR BOX — ESP32 node below-deck
17 | ESP32-S3 development board | ESP32-S3-DevKitC-1U-N8R8 | Mouser | Mouser: 356-ESP32S3DVKTC1UN8 | 1 | 12 | 12 | 1 wk | P1 | Your pick and a good one. External antenna (U.FL) version — essential for a metal/composite boat.
18 | GPS module — primary pick | SparkFun GPS-15712 (u-blox NEO-M9N) | Mouser / The Pi Hut | Mouser: 474-GPS-15712 | 1 | 53 | 53 | 1 wk | P1 | 25Hz, multi-constellation, very accurate for start-line work. Racing-grade.
19 | GPS budget alternative — keep on standby | Beitian BN-880 (u-blox NEO-M8N) | AliExpress | AliExpress: 'Beitian BN-880' | 0 | 18 | 0 | 2-3 wks | P3 | 10Hz, multi-constellation, 1/3 the price. Set qty 0 if using NEO-M9N. Good option at fleet-scale for 30 boats — £1000 saved.
20 | 9-DOF IMU (compass/heel/trim) | Adafruit BNO085 breakout | The Pi Hut | thepihut.com: 'BNO085' | 1 | 27.5 | 27.5 | 2-3 days | P1 | Onboard sensor fusion — saves you weeks of Kalman filter work. Use I2C mode.
21 | RS232/NMEA 0183 level shifter | MAX3232 breakout module | AliExpress | AliExpress: 'MAX3232 module' | 2 | 2 | 4 | 2-3 wks | P1 | Converts NMEA 0183 (±12V) to ESP32 TTL (3.3V). One for wind sensor input. Buy 2 for backup.
22 | RS485 level shifter (optional) | MAX485 breakout module | AliExpress | AliExpress: 'MAX485 module' | 2 | 2 | 4 | 2-3 wks | P2 | For any RS485 sensors (if you add depth via Modbus later, or want to run a long-run sensor network on RS485).
23 | Pressure/temp/humidity sensor | Bosch BME280 breakout | AliExpress | AliExpress: 'BME280 breakout' | 1 | 3 | 3 | 2-3 wks | P1 | Barometric pressure for weather tracking + cabin air data. I2C.
24 | Waterproof water temp probe | DS18B20 1-wire stainless | AliExpress | AliExpress: 'DS18B20 waterproof' | 1 | 3 | 3 | 2-3 wks | P2 | Sea water temperature. Dangles through the depth-sounder thru-hull or its own small fitting.
25 | Battery monitor IC | INA226 breakout | AliExpress | AliExpress: 'INA226 module' | 1 | 4 | 4 | 2-3 wks | P2 | Measures battery voltage + current draw. Useful for long races.
26 | 5V switching regulator | Murata OKI-78SR-5/1.5-W36-C | Mouser | Mouser: 811-OKI-78SR-5-15-W36C | 1 | 5.33 | 5.33 | 1 wk | P1 | Your pick — good. Drop-in replacement for a 7805 linear but 95% efficient.
27 | IP65 project enclosure | Hammond RZ0373C | Mouser | Mouser: 546-RZ0373C | 1 | 20.34 | 20.34 | 1 wk | P1 | Your pick — good. You'll upgrade to IP68 with gland + potting.
28 | Custom sensor box PCB (5 boards) | JLCPCB 2-layer | JLCPCB | jlcpcb.com | 1 | 22 | 22 | 2 wks | P2 | After breadboard prototype validates. Design in KiCad. 5 board min order.
29 | M8 waterproof panel connectors | Generic M8 4-pin IP68 | AliExpress | AliExpress: 'M8 4-pin waterproof' | 4 | 4 | 16 | 2-3 wks | P2 | For clean cable interfaces on the enclosure. 4x = power in, wind sensor in, depth in, USB/debug.
30 | Passive components kit (R/C/LED) | 0603 SMD or through-hole kit | AliExpress | AliExpress: '0603 resistor capacitor kit' | 1 | 12 | 12 | 2-3 wks | P1 | One kit covers your whole prototype phase. Buy once.
[6 empty] | Section subtotal: | 186.17
CENTRAL COMPUTER — Pi running OpenPlotter/SignalK
31 | Raspberry Pi 4 Model B 4GB | Pi 4B 4GB | The Pi Hut | thepihut.com: 'Raspberry Pi 4 4GB' | 1 | 75 | 75 | 2-3 days | P1 | 4GB is the sweet spot for running OpenPlotter + OpenCPN + SignalK + AvNav simultaneously. Pi 5 is overkill for this. Pi Zero 2 W is not enough.
32 | Official Pi PSU | Pi 4 USB-C 5.1V 3A | The Pi Hut | thepihut.com: 'Raspberry Pi 4 power supply' | 1 | 10 | 10 | 2-3 days | P1 | Generic chargers cause brown-out issues on Pi 4. Get the official one.
33 | MicroSD card | SanDisk Extreme Pro 32GB A2 | Amazon / AliExpress | Amazon: 'SanDisk Extreme Pro 32GB A2' | 1 | 12 | 12 | 1-2 days | P1 | A2 rating critical for sustained random I/O performance. Samsung Evo Plus also good.
34 | Pi 4 case with cooling | Argon NEO or FLIRC | The Pi Hut | thepihut.com: 'Argon NEO Pi 4' | 1 | 18 | 18 | 2-3 days | P1 | Aluminium passive cooling. Fan-less. Marine-appropriate. You'll add your own water-resistant outer enclosure.
35 | 12V → 5V USB-C marine converter | DROK or RIGOIL 12V-5V USB-C 3A | Amazon | Amazon: '12V to 5V USB-C marine DC-DC' | 1 | 15 | 15 | 1-2 days | P1 | Boat runs 12V. Pi needs 5V/3A USB-C. Marine-grade converter handles the voltage spikes a boat electrical system throws. Don't use a phone car charger.
36 | OPTIONAL: NMEA 2000 HAT | PICAN-M with micro-C connector | SK Pang Electronics | skpang.co.uk: 'PICAN-M' | 0 | 95 | 0 | 3-5 days | P3 | Only needed if you're integrating with other boats' existing B&G/Raymarine systems that speak NMEA 2000. Set qty 1 if yes. For all-DIY sensors stick with NMEA 0183.
[6 empty] | Section subtotal: | 130
DISPLAY — Kindle e-ink racing repeater
37 | Kindle Paperwhite (11th/12th gen) | Amazon Kindle Paperwhite | Amazon UK | Amazon: 'Kindle Paperwhite' | 1 | 150 | 150 | 1-2 days | P1 | Already IPX8 out of the box — no extra hardening needed. Use 'with ads' version to save £20, ads only show on lock screen. Browser displays SignalK/AvNav dashboard.
38 | Kindle marine-suitable silicone case | Generic Kindle case | Amazon | Amazon: 'Kindle Paperwhite silicone case' | 1 | 15 | 15 | 1-2 days | P1 | Extra impact protection + UV protection. The Kindle is waterproof but the bezel corners crack on impact.
39 | RAM X-Grip universal tablet mount | RAM-HOL-UN7BU or similar | RAM Mounts UK | rammount.co.uk: 'RAM X-Grip universal' | 1 | 45 | 45 | 3-5 days | P2 | The mount is what you buy Raymarine for. RAM makes the best. X-Grip holds any tablet/Kindle, rotates, and handles boat vibration.
40 | OPTIONAL: BOOX Palma 2 (premium path) | BOOX Palma 2 | Onyx BOOX / Amazon | boox.com: 'Palma 2' | 0 | 280 | 0 | 1-2 wks | P3 | Full Android on e-ink in a phone-size form factor. Runs any sailing app. Set qty 1 if you want premium spec. £280 vs £150 Kindle.
[6 empty] | Section subtotal: | 210
CABLES, CONNECTORS & ELECTRICAL
41 | 12V fused distribution block | Blue Sea ST Blade 6-circuit | ASAP Supplies / Amazon | ASAP: 'Blue Sea ST Blade 6' | 1 | 25 | 25 | 2-3 days | P1 | Clean power distribution for all your boxes. Marine-grade. Inline fuses for each load.
42 | Inline fuse holders | Waterproof ATO blade fuse holder x 5 | Amazon | Amazon: 'waterproof inline fuse holder' | 1 | 12 | 12 | 1-2 days | P1 | Each sensor/device gets its own fuse. Non-negotiable for marine electrical.
43 | ATO fuse assortment | 3A/5A/7.5A/10A mixed pack | Amazon | Amazon: 'ATO fuse mixed pack' | 1 | 6 | 6 | 1-2 days | P1 | Most of your stuff is 3A or 5A. Pi gets 5A. Sensors get 3A.
44 | Marine crimp terminals (waterproof) | Heat-shrink butt connectors assortment | ASAP / Amazon | Amazon: 'marine heat shrink butt connectors' | 1 | 18 | 18 | 1-2 days | P1 | Adhesive-lined heat shrink. The only marine-acceptable crimp. Avoid cheap PVC-sleeved terminals on a boat.
45 | Heat shrink tubing assortment | Black/transparent multi-size kit | AliExpress | AliExpress: 'heat shrink tube kit 3:1' | 1 | 10 | 10 | 2-3 wks | P1 | 3:1 adhesive-lined. Buy the kit — cheaper than individual sizes.
46 | Wago 221 lever connectors | Wago 221 mixed pack | Amazon / RS | Amazon: 'Wago 221 lever connector' | 1 | 18 | 18 | 1-2 days | P1 | For interior dry connections. Marine professionals hate them; in sealed dry boxes they're fine and save huge time.
47 | UV-resistant cable ties | Black nylon UV 200mm x 100 | Amazon / chandler | Amazon: 'UV resistant cable ties marine' | 1 | 8 | 8 | 1-2 days | P1 | Standard white ties fail within one season in UV.
48 | Sikaflex 291 marine sealant | Sika Sikaflex 291i (300ml) | chandler | Force4: 'Sikaflex 291' | 1 | 15 | 15 | 2-3 days | P1 | For deck penetrations and final sealing. Standard marine bedding compound.
[6 empty] | Section subtotal: | 112
ELECTRICAL PROTECTION — essential for masthead gear
49 | TVS diodes (transient protection) | SMAJ24CA (24V bidirectional) | Mouser | Mouser: 'SMAJ24CA' | 10 | 0.5 | 5 | 1 wk | P1 | Catches lightning-induced surges + alternator spikes. One on every power/signal line entering your enclosure. Buy 10 — they're tiny.
50 | Gas discharge tubes (lightning) | Littelfuse CG2-230L or similar | Mouser | Mouser: 'gas discharge tube 230V' | 4 | 3.5 | 14 | 1 wk | P1 | The first line of defence for a direct/near lightning strike on the mast. One on each conductor of the mast cable at entry to the enclosure. TVS diodes alone won't handle a real strike.
51 | Ferrite clip-on chokes | Würth 74271222 or generic clip-on | Mouser / AliExpress | AliExpress: 'ferrite clip choke 13mm' | 8 | 1 | 8 | 2-3 wks | P1 | Clip these on every cable at both ends. VHF at 156MHz will induce noise in your NMEA 0183 lines without them. Cheap insurance.
52 | Reverse polarity MOSFET protection | P-channel MOSFET (e.g. IRF9540) | Mouser | Mouser: 'IRF9540N TO-220' | 3 | 1 | 3 | 1 wk | P1 | Marine wiring gets connected backwards more often than you think. This protects against it with zero voltage drop (unlike a diode).
[6 empty] | Section subtotal: | 30
TOOLS & ONE-TIME PURCHASES (buy once, use for 30 boats)
53 | USB to NMEA 0183 adapter | Digital Yacht USB-NMEA or Actisense | Amazon / Digital Yacht | Amazon: 'USB to NMEA 0183 adapter' | 1 | 25 | 25 | 1-2 days | P1 | Critical for testing — plug into laptop to see the raw NMEA stream from your sensors during bench testing.
54 | USB to RS485 adapter | FTDI-chip USB-RS485 cable | AliExpress / Amazon | AliExpress: 'USB to RS485 FTDI' | 1 | 8 | 8 | 2-3 wks | P1 | Same but for any RS485 sensors or direct Veinasa testing.
55 | Soldering station | Generic 60W temp-controlled | Amazon | Amazon: 'soldering station 60W' | 1 | 50 | 50 | 1-2 days | P1 | Skip if you have one. Needed for PCB assembly and cable work.
56 | Multimeter | Generic auto-ranging DMM | Amazon | Amazon: 'digital multimeter' | 1 | 30 | 30 | 1-2 days | P1 | Skip if you have one. For debugging everything.
57 | Pressure test rig (for IP68 verification) | Aquarium + small aquarium pump + gauge | DIY / Amazon | Amazon: 'aquarium pump' + 'pressure gauge' | 1 | 35 | 35 | 1-2 days | P1 | Your IP68 validation setup. Submerge the sealed enclosure under 1m water, apply 0.1 bar, wait 30min, check for bubbles + moisture inside afterwards.
58 | HDMI cable + USB keyboard/mouse (Pi setup) | Any HDMI + USB combo | Amazon / already own | - | 1 | 10 | 10 | 1-2 days | P1 | Needed once to set up the Pi. After that it runs headless over WiFi.
[6 empty] | Section subtotal: | 158
GRAND TOTAL — one complete boat system: | [6 empty] | 1377.17
P1 items only — minimum to start building: | [6 empty] | 1040.17
P2 items — phase 2 after P1 validated: | [6 empty] | 337
P3 items — optional / premium (qty usually 0): | [6 empty] | 0

## 30-Boat Scaling
SCALING TO 30 BOATS — strategic considerations
Wind sensor (Veinasa) | At qty 30, contact Sichuan Weinasa Technology directly (sales@weinasa.com or via Alibaba). Expect ~$140-150 per unit (vs $199 AliExpress retail). Also negotiate: (1) 4Hz firmware, (2) factory calibration certificate per unit, (3) custom colour/branding if you want to white-label.
Depth sounder | For 30 units the DIY Open Echo route becomes painful (30x PCB assembly, 30x potting). Switch to the Chinese OVA A-P319N at ~£100 each (vs £75 DIY labour-inclusive). Your lab time is worth more than £25/unit. Keep DIY for the prototype and first 2-3 units only.
Raspberry Pi | Pi stock fluctuates. Order all 30 Pis together or buy from a volume reseller. Consider Pi Compute Module 4 + custom carrier board if you want a truly integrated product — ~£50/unit for the module but you design your own PCB with connectors, regulator, RTC all built in.
Kindle Paperwhites | Buy 35 Kindles (30 + spares) as a business via Amazon Business for ~10% discount. Alternatively buy second-hand/refurbished — a 2-year-old Paperwhite is indistinguishable and £60-80 each.
PCB manufacturing | At qty 30 order PCBs + SMT assembly from JLCPCB in a single batch. 30 boards + assembly typically £15-25 per assembled board (vs £40-50 for a one-off). 2-week lead time. Saves you hand-assembly labour.
IP68 hardening batch process | Set up a single pour-and-cure session per week: 10 sensor assemblies per weekend. Conformal coat batch in the morning, potting in the afternoon. Label and log each unit with a serial number — essential for warranty/support later.
Cables & consumables | Order in bulk: 500m reel of 4-core shielded cable is ~£500 (vs 30 × 20m = £600 cut-length). Fuse holders, terminals, cable ties all drop 40-50% at pack sizes of 100+.
Fleet-wide software | Only one copy of every software piece needed (OpenPlotter/OpenCPN/SignalK are free). However, consider setting up: (1) a master Pi image you clone to SD cards, (2) a fleet-management dashboard so owners can update firmware OTA, (3) a shared chart cache + marker buoy database — this is where your 30-boat deployment gets interesting for racing.
Support & warranty | 30 boats means 30 potential support calls. Budget: swap-out spare sensor node (pre-built) ready for anyone whose box dies. £200 in inventory saves a race weekend. Include a pre-paid return envelope with every unit sold.
Pricing for resale | Rough cost at qty 30: £650-750 per boat (parts). Lab assembly labour: estimate 8-10 hours/boat at £25/hr = £200-250. Total cost ~£900-1000/boat. Market price to your 30 local boats: £1500-1800 (still half of B&G, and they know you personally). Gross margin of ~£500-700 per boat, funding your ongoing development.
IP/licensing risk | Your software stack is GPL (OpenCPN), Apache 2 (SignalK), MIT/similar. If you sell units you must make your source code + any modifications available. This is usually a strength ('open so you can modify yourself') not a weakness. Check Veinasa's OEM terms — they may have conditions on reselling their hardware integrated into a product.

## Order Timeline
ORDER TIMELINE — what to buy when
When | Action | Detail
Day 0 | Order Week 1 batch — UK fast items | Kindle Paperwhite, Raspberry Pi 4 + PSU + SD + case, Pi Hut items (BNO085, ESP32-S3), all Mouser items (NEO-M9N, OKI-78SR-5, Hammond enclosure, TUSS4470 ICs, TVS diodes, GDTs). These arrive in 1-5 days and let you start building the software/central computer side immediately.
Day 0 | Order Week 1 batch — AliExpress / Alibaba slow items | Veinasa CXS02B-N NMEA 0183 (x2), 200kHz depth transducer (x3), MAX3232/MAX485 modules, MT3608 converters, BME280, DS18B20, INA226, Arduino Nano clones, passives kit, M8 connectors, heat shrink, ferrite chokes. 3-4 weeks lead — order today so they arrive when you're ready for them.
Week 1 | Start: Pi + OpenPlotter setup | While AliExpress ships, set up OpenPlotter on the Pi. Install SignalK + OpenCPN + AvNav. Generate fake NMEA data with a Python script to feed SignalK. Point Kindle browser at the AvNav URL. You'll have a working display pipeline before any real sensor arrives.
Week 1 | Order consumables / ASAP Supplies | Marine cable, fuse blocks, crimp terminals, Sikaflex, cable glands, distribution block. ASAP Supplies UK ships in 2-3 days.
Week 2 | Prototype sensor box on breadboard | When ESP32/GPS/BNO085 arrive — wire up on breadboard, get them reporting into SignalK. Test with fake NMEA wind data. This validates the ESP32 firmware + SignalK integration.
Week 3-4 | Anemometer arrives — wind sensor integration | Wire Veinasa → MAX3232 → ESP32 → WiFi → SignalK. Should just be reading NMEA MWV sentences. Test outdoors on a pole before committing to masthead install.
Week 4 | Build the Open Echo depth sounder | Breadboard the TUSS4470 + 200kHz transducer. Test in a bucket first (expect 10-30cm reading). Then a swimming pool. Then a marina. Don't skip these stages.
Week 5-6 | Design custom PCBs | Once both sensors work on breadboard, design proper PCBs in KiCad. Order 5-board batch from JLCPCB. Order assembled if you've got SMT parts you can't hand-solder.
Week 6-8 | IP68 hardening trials | Conformal coat + pot the first prototype enclosures. Pressure-test to 1m water column. Iterate on gland/cable sealing until zero leaks over 30 minutes at 0.1 bar.
Week 8+ | First on-water test | Install in one boat. Race with it. Break it. Fix it. Race again. Document everything that goes wrong — these become your installation manual.
Month 3-4 | Scale decision gate | Do you have a stable, tested single-boat system? If yes, start the qty 30 bulk order. If no, keep iterating. DO NOT order 30 of anything until one works for a whole season.